## Overview
ACME CORP
Acme HQ Office Renovation
Status as of 19 April 2026
OVERALL COMPLETE | MILESTONES | SCHEDULE HEALTH | TARGET HANDOVER
28% | 2 of 9 | At risk | 25 Sep 2026
STATUS SUMMARY
Design phase substantially complete. Permits are the current critical path with a five-day slip — mobilisation for construction is still tracking to 4 May.
PROJECT DETAIL
Client | Acme Corp
Project manager | Benjamin Vermeulen
Start | 02 March 2026
End | 25 September 2026
Duration | 207 days
Generated | 2026-04-19
Prepared by Benjamin Vermeulen • Generated 2026-04-19

## Gantt
ACME CORP
Schedule
Weekly resolution • Status as of 19 April 2026
|  |  |  | MAR 2026 |  |  |  |  | APR 2026 |  |  |  | MAY 2026 |  |  |  | JUN 2026 |  |  |  |  | JUL 2026 |  |  |  | AUG 2026 |  |  |  |  | SEP 2026
TASK | OWNER | START | PROGRESS | 02 | 09 | 16 | 23 | 30 | 06 | TODAY | 20 | 27 | 04 | 11 | 18 | 25 | 01 | 08 | 15 | 22 | 29 | 06 | 13 | 20 | 27 | 03 | 10 | 17 | 24 | 31 | 07 | 14 | 21
MILESTONES
◆ Concept design approved | Architect | 27 Mar | Achieved |  |  |  | ◆
◆ Detailed design sign-off | Architect | 17 Apr | Achieved | [6 empty] | ◆
◆ Permits approved | Permit Consultant | 30 Apr | At risk | [8 empty] | ◆
◆ Contractor appointed | PM | 01 May | On track | [8 empty] | ◆
◆ Site handover | Contractor | 08 May | On track | [9 empty] | ◆
◆ Structural alterations complete | Structural Engineer | 19 Jun | On track | [15 empty] | ◆
◆ MEP first fix complete | Contractor | 24 Jul | On track | [20 empty] | ◆
◆ Practical completion | PM | 15 Sep | On track | [28 empty] | ◆
◆ Handover to client | PM | 25 Sep | On track | [29 empty] | ◆
DESIGN & PERMITS
Programme & brief | PM | 02 Mar | 100%
Concept design | Architect | 16 Mar | 100%
Detailed design | Architect | 30 Mar | 100%
Permit applications | Permit Consultant | 06 Apr | 55%
Tender & contractor selection | PM | 13 Apr | 35%
DEMOLITION & STRUCTURAL
Site handover & mobilisation | Contractor | 04 May | 0%
Demolition | Contractor | 11 May | 0%
Structural alterations | Structural Engineer | 01 Jun | 0%
FIT-OUT & SERVICES
MEP first fix | Contractor | 22 Jun | 0%
Partitions & ceilings | Contractor | 13 Jul | 0%
Finishes | Contractor | 03 Aug | 0%
FF&E installation | FF&E Supplier | 17 Aug | 0%
SNAGGING & HANDOVER
Commissioning | Contractor | 31 Aug | 0%
Snagging & client sign-off | PM | 14 Sep | 0%
Note on I9: Concept design approved — 27 March 2026 (Achieved)
Note on L10: Detailed design sign-off — 17 April 2026 (Achieved)
Note on N11: Permits approved — 30 April 2026 (At risk)
Note on N12: Contractor appointed — 01 May 2026 (On track)
Note on O13: Site handover — 08 May 2026 (On track)
Note on U14: Structural alterations complete — 19 June 2026 (On track)
Note on Z15: MEP first fix complete — 24 July 2026 (On track)
Note on AH16: Practical completion — 15 September 2026 (On track)
Note on AI17: Handover to client — 25 September 2026 (On track)

## Milestones
ACME CORP
Milestone tracker
Status as of 19 April 2026
ID | MILESTONE | DATE | STATUS | OWNER | DESCRIPTION
M01 | Concept design approved | 27 Mar 2026 | Achieved | Architect | Client signed off the concept design and footprint.
M02 | Detailed design sign-off | 17 Apr 2026 | Achieved | Architect | Detailed drawings, spec, and FF&E schedule approved.
M03 | Permits approved | 30 Apr 2026 | At risk | Permit Consultant | City sign-off on building and mechanical permits. Currently five working days behind the target date.
M04 | Contractor appointed | 01 May 2026 | On track | PM | Signed main contract with preferred contractor.
M05 | Site handover | 08 May 2026 | On track | Contractor | Physical handover of the building to the main contractor for works.
M06 | Structural alterations complete | 19 Jun 2026 | On track | Structural Engineer | All demolition and structural changes signed off by the engineer.
M07 | MEP first fix complete | 24 Jul 2026 | On track | Contractor | Mechanical, electrical, and plumbing first fix signed off.
M08 | Practical completion | 15 Sep 2026 | On track | PM | Building is safe to occupy; snag list issued.
M09 | Handover to client | 25 Sep 2026 | On track | PM | All snags cleared, documentation and warranties transferred.

## Review needed
ACME CORP
Review needed
Items surfaced for explicit review before sending to the client.
SCOPE | REF | REASON
milestones | M03 | Permit sign-off is trending five working days behind the internal target. Recommend the client clears a pre-meeting slot with the city permits office in the next ten days to de-risk the 30 April date.