## Slide 1
ACME CORP · PROJECT PLAN
Acme HQ Office Renovation
Design phase substantially complete. Permits are the current critical path with a five-day slip — mobilisation for construction is still tracking to 4 May.
CLIENT
Acme Corp
PROJECT MANAGER
Benjamin Vermeulen
STATUS AS OF
19 April 2026
Acme Corp · Acme HQ Office Renovation · Status as of 19 April 2026
01 / 08

## Slide 2
EXECUTIVE SNAPSHOT
Where the project stands today
OVERALL COMPLETE
26%
Duration-weighted average
MILESTONES
2 / 9
Achieved to date
NEXT MILESTONE
30 Apr
Permits approved
SCHEDULE HEALTH
Watch
1 task(s) at risk
Design phase substantially complete. Permits are the current critical path with a five-day slip — mobilisation for construction is still tracking to 4 May.
Acme Corp · Acme HQ Office Renovation · Status as of 19 April 2026
02 / 08

## Slide 3
TIMELINE
Phases at a glance
Mar 2026
Apr 2026
May 2026
Jun 2026
Jul 2026
Aug 2026
Sep 2026
MILESTONES
27 Mar
17 Apr
30 Apr
8 May
19 Jun
24 Jul
15 Sep
25 Sep
Design & Permits
2 Mar — 1 May
73% complete
Demolition & Structural
4 May — 19 Jun
0% complete
Fit-out & Services
22 Jun — 28 Aug
0% complete
Snagging & Handover
31 Aug — 25 Sep
0% complete
TODAY
Acme Corp · Acme HQ Office Renovation · Status as of 19 April 2026
03 / 08

## Slide 4
DETAIL SCHEDULE
Task-level Gantt
MAR
APR
MAY
JUN
JUL
AUG
SEP
MILESTONES
27 Mar
17 Apr
30 Apr
8 May
19 Jun
24 Jul
15 Sep
25 Sep
Programme & brief
PM
Concept design
Architect
Detailed design
Architect
Permit applications
Permit Consultant
Tender & contractor selection
PM
Site handover & mobilisation
Contractor
Demolition
Contractor
Structural alterations
Structural Engineer
MEP first fix
Contractor
Partitions & ceilings
Contractor
Finishes
Contractor
FF&E installation
FF&E Supplier
TODAY
Shaded bar: remaining · Accent fill: complete · Warm fill: at risk
Acme Corp · Acme HQ Office Renovation · Status as of 19 April 2026
04 / 08

## Slide 5
MILESTONES
Milestone tracker
17 APRIL 2026
Detailed design sign-off
Detailed drawings, spec, and FF&E schedule approved.
Achieved
30 APRIL 2026
Permits approved
City sign-off on building and mechanical permits. Currently five working days behind the target date.
At risk
1 MAY 2026
Contractor appointed
Signed main contract with preferred contractor.
On track
8 MAY 2026
Site handover
Physical handover of the building to the main contractor for works.
On track
19 JUNE 2026
Structural alterations complete
All demolition and structural changes signed off by the engineer.
On track
24 JULY 2026
MEP first fix complete
Mechanical, electrical, and plumbing first fix signed off.
On track
Acme Corp · Acme HQ Office Renovation · Status as of 19 April 2026
05 / 08

## Slide 6
NEXT FORTNIGHT
What lands in the next 14 days
Tasks completing
30 Apr
Permit applications
Permit Consultant
1 May
Tender & contractor selection
PM
Milestones in window
30 Apr
Permits approved
Permit Consultant
At risk
1 May
Contractor appointed
PM
On track
Acme Corp · Acme HQ Office Renovation · Status as of 19 April 2026
06 / 08

## Slide 7
REVIEW NEEDED
Items that need a decision
Bring these to the project review — each one needs a client decision or an escalation to keep the plan on track.
MILESTONES · M03
Permit sign-off is trending five working days behind the internal target. Recommend the client clears a pre-meeting slot with the city permits office in the next ten days to de-risk the 30 April date.
Acme Corp · Acme HQ Office Renovation · Status as of 19 April 2026
07 / 08

## Slide 8
HANDOVER
Questions, or somewhere you'd like me to dig deeper?
This deck pairs with a spreadsheet and an interactive HTML view covering the same plan at full resolution. Both ship with the package for your records.
PROJECT MANAGER
Benjamin Vermeulen
Acme Corp · Acme HQ Office Renovation
Acme Corp · Acme HQ Office Renovation · Status as of 19 April 2026
08 / 08